## Example
Acme Widget Co.
Client Commitment Action Plan
Task | Scope Reference | Assigned to | Due Date | Status | Date Completed
update projections for YTD actuals - mid year | Section 1 (a) | sub controllers | 2018-07-31
complete merger - legal & accounting | Section 3 (b) | RLS | 2018-08-31
close BOA bank accounts |  | Mike | 2018-06-15
develop standard reporting package for subs |  | JRW/JK | 2018-06-25 | Done | 2018-07-15
address negative cash flow @ sub level |  | JRW/JK | 2018-07-01
outsource 401k & medical function |  | JRW/JK | 2018-07-31 | In progress
outsource HR function |  | JRW/JK | 2018-07-31 | In progress
prepare borrowing base availability by entity |  | JRW | 2018-06-07
review & revise weekly cash reporting - project needs |  | JRW | 2018-06-07 | Done | 2018-06-15
review cash management - restructure |  | JRW | 2018-06-07 | In progress
standardize daily cash reports - subs prepare |  | JRW | 2018-06-07 | Done | 2018-06-15
reorganize debt - push to subs |  | JRW | 2018-08-01
research PEO for payroll; medical benefits; 401K |  | JK | 2018-06-30 | In progress
project cash needs 90 days @ sub level |  | JK | 2018-07-01
reorganize P&C insurance - push to subs |  | JK | 2018-07-01
reassign preparation of quarterly financial statements |  | JK | 2018-07-30 | Done | 2018-07-18
reduce # of bank accounts @ corporate office |  | JK | 2018-07-31 | In progress
address Joe & Lesli - corporate payroll |  | JK | 2018-08-01
complete 2018 audit - Acme Corp |  | DT/Bob | 2018-07-01 | Done | 2018-07-18
complete 2018 audit - Acme Manufacturing |  | DT/Bob | 2018-07-01 | Done | 2018-07-18
complete 2018 audit - Acme Solutions |  | DT/Bob | 2018-07-01 | Done | 2018-07-18
complete 2018 tax returns |  | DT/Bob | 2018-08-01
complete 2018 audit - ACME Corp |  | DT/Bob | 2018-08-15
research yacht management co |  | TJ | 2018-09-01
set up books for recently completed special purpose entities |  | TJ | 2018-09-01 | In Progress
finalize accounting for entities sold |  | TJ | 2018-10-30
fixed assets: distribute to subs |  | TJ | 2018-11-30
simplify legal structure |  | TJ | 2018-12-31
outsource plane management |  | TJ | 2019-01-31

## Action Plan
Insert Your Company Name Here
Action Plan
Project Name
Task | Assigned To | Due Date | Status | Date Completed